## Sprint burndown
|  |  | This is a task based burn down. The most common. | [9 empty] | Name: | Building Rome in 30 days
Complete the Task weighting grid by adding task name and weight %
Then add the task IDs to the Estimated column based on planned completion
Then add the task IDs to the Actual column based on actual completion
Drag down the Actual % column to show progress
Task inventory |  |  | Task completion log | [8 empty] | Burndown graph
|  |  | Completed tasks | [6 empty] | Task completion (%)
|  |  | Projected |  |  | Actual |  |  |  | Projected | Actual
ID | Name | Weight (%) | Task ID | Data | Cum | Task ID | Data | Cum | Date |  | Actual
1 | Pick up bricks | 6% |  | 0% |  |  | 0% |  | 2013-02-16 | 100% | 100%
2 | Apply mortar | 6% | 1 | 6% | 6% |  | 0% | 0% | 2013-02-17 | 94% | 100%
3 | Collect materials | 6% |  | 0% | 6% |  | 0% | 0% | 2013-02-18 | 94%
4 | Pay foreman | 10% | 2 | 6% | 12% |  | 0% | 0% | 2013-02-19 | 88%
5 | Meet centurian | 5% |  | 0% | 12% |  | 0% | 0% | 2013-02-20 | 88%
6 | Lay first wall | 15% | 3 | 6% | 18% |  | 0% | 0% | 2013-02-21 | 82%
7 | Lay garden | 15% |  | 0% | 18% |  | 0% | 0% | 2013-02-22 | 82%
8 | Attend senate session | 15% | 4 | 10% | 28% |  | 0% | 0% | 2013-02-23 | 72%
9 | Erect statues | 2% |  | 0% | 28% |  | 0% | 0% | 2013-02-24 | 72%
10 | Buy next batch of bricks | 5% | 5 | 5% | 33% |  | 0% | 0% | 2013-02-25 | 67%
11 | Complete drainage | 1% |  | 0% | 33% |  | 0% | 0% | 2013-02-26 | 67%
12 | Install aquaduct | 6% | 6 | 15% | 48% |  | 0% | 0% | 2013-02-27 | 52%
13 | Hire musical entertainment | 4% |  | 0% | 48% |  | 0% | 0% | 2013-02-28 | 52%
14 | Buy wine | 2% | 7 | 15% | 63% |  | 0% | 0% | 2013-03-01 | 37%
15 | Celebrate opening | 2% |  | 0% | 63% |  | 0% | 0% | 2013-03-02 | 37%
|  |  | 8 | 15% | 78% |  | 0% | 0% | 2013-03-03 | 22%
|  |  |  | 0% | 78% |  | 0% | 0% | 2013-03-04 | 22%
|  |  | 9 | 2% | 80% |  | 0% | 0% | 2013-03-05 | 20%
|  |  |  | 0% | 80% |  | 0% | 0% | 2013-03-06 | 20%
|  |  | 10 | 5% | 85% |  | 0% | 0% | 2013-03-07 | 15%
|  |  |  | 0% | 85% |  | 0% | 0% | 2013-03-08 | 15%
|  |  | 11 | 1% | 86% |  | 0% | 0% | 2013-03-09 | 14%
|  |  |  | 0% | 86% |  | 0% | 0% | 2013-03-10 | 14%
|  |  | 12 | 6% | 92% |  | 0% | 0% | 2013-03-11 | 8%
|  |  |  | 0% | 92% |  | 0% | 0% | 2013-03-12 | 8%
|  |  | 13 | 4% | 96% |  | 0% | 0% | 2013-03-13 | 4%
|  |  | 14 | 2% | 98% |  | 0% | 0% | 2013-03-14 | 2%
|  |  |  | 0% | 98% |  | 0% | 0% | 2013-03-15 | 2%
|  |  | 15 | 2% | 100% |  | 0% | 0% | 2013-03-16 | -2.22e-14%
| must equal 100 > | 100%
<< Remove cells not in use, copy down additional cells if you need more then update the graph to include/exclude them
Formulas:
Date = [Date, row above]+1

## Burndown with actual formula
|  |  | This is a task based burn down. The most common. | [9 empty] | Name: | Building Rome in 30 days
Complete the Task weighting grid by adding task name and weight %
Then add the task IDs to the Estimated column based on planned completion
Then add the task IDs to the Actual column based on actual completion
Task inventory |  |  | Task completion log | [8 empty] | Burndown graph
|  |  | Completed tasks | [6 empty] | Task completion (%)
|  |  | Projected |  |  | Actual |  |  |  | Projected | Actual
ID | Name | Weight (%) | Task ID | Data | Cum | Task ID | Data | Cum | Date |  | Actual
1 | Pick up bricks | 6% |  | 0% |  |  | 0% |  | 2013-02-16 | 100% | 100%
2 | Apply mortar | 6% | 1 | 6% | 6% |  | 0% | 0% | 2013-02-17 | 94% | 100%
3 | Collect materials | 6% |  | 0% | 6% |  | 0% | 0% | 2013-02-18 | 94% | 100%
4 | Pay foreman | 10% | 2 | 6% | 12% |  | 0% | 0% | 2013-02-19 | 88% | 100%
5 | Meet centurian | 5% |  | 0% | 12% |  | 0% | 0% | 2013-02-20 | 88% | 100%
6 | Lay first wall | 15% | 3 | 6% | 18% |  | 0% | 0% | 2013-02-21 | 82% | 100%
7 | Lay garden | 15% |  | 0% | 18% |  | 0% | 0% | 2013-02-22 | 82% | 100%
8 | Attend senate session | 15% | 4 | 10% | 28% |  | 0% | 0% | 2013-02-23 | 72% | 100%
9 | Erect statues | 2% |  | 0% | 28% |  | 0% | 0% | 2013-02-24 | 72% | 100%
10 | Buy next batch of bricks | 5% | 5 | 5% | 33% |  | 0% | 0% | 2013-02-25 | 67% | 100%
11 | Complete drainage | 1% |  | 0% | 33% |  | 0% | 0% | 2013-02-26 | 67% | 100%
12 | Install aquaduct | 6% | 6 | 15% | 48% |  | 0% | 0% | 2013-02-27 | 52% | 100%
13 | Hire musical entertainment | 4% |  | 0% | 48% |  | 0% | 0% | 2013-02-28 | 52% | 100%
14 | Buy wine | 2% | 7 | 15% | 63% |  | 0% | 0% | 2013-03-01 | 37% | 100%
15 | Celebrate opening | 2% |  | 0% | 63% |  | 0% | 0% | 2013-03-02 | 37% | 100%
|  |  | 8 | 15% | 78% |  | 0% | 0% | 2013-03-03 | 22% | 100%
|  |  |  | 0% | 78% |  | 0% | 0% | 2013-03-04 | 22% | 100%
|  |  | 9 | 2% | 80% |  | 0% | 0% | 2013-03-05 | 20% | 100%
|  |  |  | 0% | 80% |  | 0% | 0% | 2013-03-06 | 20% | 100%
|  |  | 10 | 5% | 85% |  | 0% | 0% | 2013-03-07 | 15% | 100%
|  |  |  | 0% | 85% |  | 0% | 0% | 2013-03-08 | 15% | 100%
|  |  | 11 | 1% | 86% |  | 0% | 0% | 2013-03-09 | 14% | 100%
|  |  |  | 0% | 86% |  | 0% | 0% | 2013-03-10 | 14% | 100%
|  |  | 12 | 6% | 92% |  | 0% | 0% | 2013-03-11 | 8% | 100%
|  |  |  | 0% | 92% |  | 0% | 0% | 2013-03-12 | 8% | 100%
|  |  | 13 | 4% | 96% |  | 0% | 0% | 2013-03-13 | 4% | 100%
|  |  | 14 | 2% | 98% |  | 0% | 0% | 2013-03-14 | 2% | 100%
|  |  |  | 0% | 98% |  | 0% | 0% | 2013-03-15 | 2% | 100%
|  |  | 15 | 2% | 100% |  | 0% | 0% | 2013-03-16 | -2.22e-14% | 100%
| must equal 100 > | 100%
<< Remove cells not in use, copy down additional cells if you need more then update the graph to include/exclude them
Formulas:
Date = [Date, row above]+1

## Completed
|  |  | This is a task based burn down. The most common. | [9 empty] | Name: | Building Rome in 30 days
Complete the Task weighting grid by adding task name and weight %
Then add the task IDs to the Estimated column based on planned completion
Then add the task IDs to the Actual column based on actual completion
Drag down the Actual % column to show progress
3
Task inventory |  |  | Task completion log | [8 empty] | Burndown graph
|  |  | Completed tasks | [6 empty] | Task completion (%)
|  |  | Projected |  |  | Actual |  |  |  | Projected | Actual
ID | Name | Weight (%) | Task ID | Data | Cum | Task ID | Data | Cum | Date |  | Actual
1 | Pick up bricks | 6% |  | 0% |  |  | 0% |  | 2018-02-16 | 100% | 100%
2 | Apply mortar | 6% | 1 | 6% | 6% |  | 0% | 0% | 2018-02-17 | 94% | 100%
3 | Collect materials | 6% |  | 0% | 6% | 1 | 6% | 6% | 2018-02-18 | 94% | 94%
4 | Pay foreman | 10% | 2 | 6% | 12% | 2 | 6% | 12% | 2018-02-19 | 88% | 88%
5 | Meet centurian | 5% |  | 0% | 12% |  | 0% | 12% | 2018-02-20 | 88% | 88%
6 | Lay first wall | 15% | 3 | 6% | 18% | 3 | 6% | 18% | 2018-02-21 | 82% | 82%
7 | Lay garden | 15% |  | 0% | 18% |  | 0% | 18% | 2018-02-22 | 82% | 82%
8 | Attend senate session | 15% | 4 | 10% | 28% | 4 | 10% | 28% | 2018-02-23 | 72% | 72%
9 | Erect statues | 2% |  | 0% | 28% | 5 | 5% | 33% | 2018-02-24 | 72% | 67%
10 | Buy next batch of bricks | 5% | 5 | 5% | 33% | 6 | 15% | 48% | 2018-02-25 | 67% | 52%
11 | Complete drainage | 1% |  | 0% | 33% |  | 0% | 48% | 2018-02-26 | 67% | 52%
12 | Install aquaduct | 6% | 6 | 15% | 48% | 7 | 15% | 63% | 2018-02-27 | 52% | 37%
13 | Hire musical entertainment | 4% |  | 0% | 48% | 8 | 15% | 78% | 2018-02-28 | 52% | 22%
14 | Buy wine | 2% | 7 | 15% | 63% |  | 0% | 78% | 2018-03-01 | 37% | 22%
15 | Celebrate opening | 2% |  | 0% | 63% |  | 0% | 78% | 2018-03-02 | 37% | 22%
|  |  | 8 | 15% | 78% | 9 | 2% | 80% | 2018-03-03 | 22% | 20%
|  |  |  | 0% | 78% | 10 | 5% | 85% | 2018-03-04 | 22% | 15%
|  |  | 9 | 2% | 80% | 11 | 1% | 86% | 2018-03-05 | 20% | 14%
|  |  |  | 0% | 80% |  | 0% | 86% | 2018-03-06 | 20% | 14%
|  |  | 10 | 5% | 85% |  | 0% | 86% | 2018-03-07 | 15% | 14%
|  |  |  | 0% | 85% | 12 | 6% | 92% | 2018-03-08 | 15% | 8%
|  |  | 11 | 1% | 86% | 13 | 4% | 96% | 2018-03-09 | 14% | 4%
|  |  |  | 0% | 86% |  | 0% | 96% | 2018-03-10 | 14% | 4%
|  |  | 12 | 6% | 92% | 14 | 2% | 98% | 2018-03-11 | 8% | 2%
|  |  |  | 0% | 92% | 15 | 2% | 100% | 2018-03-12 | 8% | -2.22e-14%
|  |  | 13 | 4% | 96% |  | 0% | 100% | 2018-03-13 | 4% | 0%
|  |  | 14 | 2% | 98% |  | 0% | 100% | 2018-03-14 | 2% | 0%
|  |  |  | 0% | 98% |  | 0% | 100% | 2018-03-15 | 2% | 0%
|  |  | 15 | 2% | 100% |  | 0% | 100% | 2018-03-16 | -2.22e-14% | 0%
| must equal 100 > | 100%
<< Remove cells not in use, copy down additional cells if you need more then update the graph to include/exclude them
Formulas:
Date = [Date, row above]+1